## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1 | Comment2
3648305 | 68344 | ATM Project | 18 | ATM_1-18 | 292689 | Bug | 92565 | Manuel Testing | 63776 | 1.0 | performs a legitimate transfer transaction properly | MFT a) System performs a legitimate transfer transaction properly b)System is displaying a request for the customer to type a dollar amount c) Insert a card, input card number , then the correct pin. Next select 3 for transfer , select transfer from checking account to saving , enter a legitimate deposit, click insert envelope. d)System prints a correctreceipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back). e) Everything was printed, however the outut were wrong. For example when a transfer of $10 was made this was the result. The receipt read as follows:"Transfer from: Saving To CHKG ". which is incorrect. So if the Total Balance of $1010.00 and an available of $1010.00 | 3 | Resolved | 3 | Normal | 63776 | 1.0 |  |  | 319848 | Isaiah | 319848 | Isaiah | Jan. 25, 2022 11:43 |  | 319848 | Isaiah | Jan. 27, 2022 12:00 | 0 | 0 | Jan. 25, 2022 16:26 Isaiah Defect still exists in version 1.1 Transfered $10.00 from saving to checking The total balance: $1010.00 The available: $1010.00 This available balance is still incorrect
3644947 | 68344 | ATM Project | 12 | ATM_1-12 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Testing the total balance withdraw functionality Saving | a) We peformed a test on the ability to withdraw money from the ATM in the saving account. b) The system was on and idle, waiting for a withdraw. c) input 1 mutliple of $20, the ATM was on, Card 1 was entered , and then we inserted the PIN# 42, which is the correct password for Card 1 . Next, we press withdraw button and then any of the 5 buttons to select the amount we want withdraw. d) We expect the actual amount we requested to be withdrawal from the account. So if $20 was withdrawal then $20 should be removed from the account e) However, an incorrect withdrawal takes place. The amount that is withdrawal is incremented from the button pressed. For example, if 1 was pressed to withdraw $20, $40 is acutally withdrawal. | 3 | Resolved | 3 | Normal | 63776 | 1.0 |  |  | 319848 | Isaiah | 319848 | Isaiah | Jan. 24, 2022 16:10 |  | 319848 | Isaiah | Jan. 25, 2022 17:14 | 0 | 0 | Jan. 25, 2022 16:40 Isaiah The total balance and available is $980 when you withdraw $20.00 from saving
3644989 | 68344 | ATM Project | 15 | ATM_1-15 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Testing if available balance is correct after depositing into checking | a) Checking that available balance in the ATM is correctly calculated. b) The system was on and idle, waiting for a deposit in the checking account. c) input 20 mutliple of $20, the ATM was on, Card 1 was entered , and then we inserted the PIN# 42, which is the correct password for Card 1 . Next, we press the depositing button, selected the checking account and then deposited $10.(Was also performed on Card 2, with a pin# of 1234) d) we excepted an available balance of $200 e) What we got an available balance of $100. The available balance did not change Manual Test#22 | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319848 | Isaiah | 319848 | Isaiah | Jan. 24, 2022 16:53 |  | 319848 | Isaiah | Jan. 25, 2022 16:52 | 0 | 0 | Jan. 25, 2022 16:51 Isaiah Defect still exists in version 1.1 The total balance is $119.90 which is still wrong
3644971 | 68344 | ATM Project | 14 | ATM_1-14 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Testing if after withdrawing from Card 2 money market the available balance is correct | a) Checking that available balance in the ATM is correctly calculated. b) The system was on and idle, waiting for a withdraw. c) input 1 mutliple of $20, the ATM was on, Card 2 was entered , and then we inserted the PIN# 1234, which is the correct password for Card 2 . Next, we press withdraw button,pressing deposit account and then to selecting the right button to withdraw $60. d) we expect a total balance and aviavlablance balance of $4980 e) insufficient cash available | 2 | In Progress | 3 | Normal |  |  |  |  | 319848 | Isaiah | 319848 | Isaiah | Jan. 24, 2022 16:34 |  | 319848 | Isaiah | Jan. 25, 2022 16:47 | 0 | 0 | Jan. 25, 2022 16:47 Isaiah Defect still exists in version 1.1 The error is still the same
3644946 | 68344 | ATM Project | 11 | ATM_1-11 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Receipt Information Test | a) The functionality being tested is the receipt information display after a transaction of any type. b) The initial state is the machine being on and displaying any of the 4 transaction types. c) Turn the machine on and input any amount of $20 bills. Then input card 1 and the PIN 42. Perform any transaction and look at the receipt. d) The expected output is that the receipt would display Card 1 Trans #X with X being the transaction number. e) The actual output turned out to always say Card 2 Trans #X. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319847 | Aninda Shome | 319847 | Aninda Shome | Jan. 24, 2022 16:09 |  | 319847 | Aninda Shome | Jan. 25, 2022 16:37 | 0 | 0 | Jan. 25, 2022 16:37 Aninda Shome Defect still exists in version 1.1.
3644994 | 68344 | ATM Project | 16 | ATM_1-16 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Testing the total balance amount after depositing in Card (1orCard 2) | a) Performed a deposit on the checking account to see if the total balance in the ATM is correctly calculated. b) The system was on and idle, waiting for a deposit in the checking account. c) input 20 mutliple of $20, the ATM was on, Card 1 was entered , and then we inserted the PIN# 42, which is the correct password for Card 1 . Next, we press the depositing button, selected the checking account and then deposited $40.(Was also performed on Card 2, with a pin# of 1234) d) we excepted an current balance of $140 e) What we got, however, was an current balance of $130. The available balance was incorrect | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319848 | Isaiah | 319848 | Isaiah | Jan. 24, 2022 16:58 |  | 319848 | Isaiah | Jan. 25, 2022 16:36 | 0 | 0 | Jan. 25, 2022 16:35 Isaiah Defect still exists in version 1.1 Amount deposit into checking is: $20.00 THe total Balance is $119.90
3644943 | 68344 | ATM Project | 9 | ATM_1-9 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Transfer Money Test 2 | a) The functionality being tested was the transfer money feature. b) The initial state of the system is on, and it is displaying the transfer money menu. c) Turn the machine on and input any amount of $20 bills. Then insert card 1 and enter the PIN 42. Next go to option 3 (transfer) and choose to transfer from savings(2) to checking(1). Transfer $20. d) The expected outcome was that the receipt would display that the money is being transferred from savings to checking. e) The actual output was that the receipt said it transferred from checking to savings. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319847 | Aninda Shome | 319847 | Aninda Shome | Jan. 24, 2022 16:06 |  | 319847 | Aninda Shome | Jan. 25, 2022 16:34 | 0 | 0 | Jan. 25, 2022 16:34 Aninda Shome Defect still exists in version 1.1.
3644953 | 68344 | ATM Project | 13 | ATM_1-13 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Withdraw Test | a. Withdraw money from the Checkings account of Card 1. b. The system is on the Amount of cash to withdraw screen after selecting Withdrawal as the transaction type and the Checkings account as the account to withdraw from. c. Turn on the system and input 5 as the amount of $20 bills. Insert card 1 and input PIN as 42. On the transaction type screen, input transaction type 1. Then, input 1 to try and withdraw money from the checkings account. Lastly, input either of the following: 6, 7, 8, 9, or 0. d. An invalid input (6, 7, 8, 9, 0) is put in as the amount of money to withdraw from the Checkings account. This should either display that an invalid number was inputted or that the withdrawal cannot be completed. e. The ATM dispenses $20.00 and does nothing else. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319849 | Sanchit | 319849 | Sanchit | Jan. 24, 2022 16:14 |  | 319849 | Sanchit | Jan. 25, 2022 16:33 | 0 | 0 | Jan. 25, 2022 16:33 Sanchit Defect still exists in version 1.1 7, 8, 9, 0 do not do anything. 6 still dispenses $20 and does nothing else.
3644939 | 68344 | ATM Project | 7 | ATM_1-7 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Transferring Money Test | a) The functionality being tested was the transfer money feature. b) The initial state of the system is on, and it is displaying the transfer money menu. c) Turn the machine on and input any amount of $20 bills. Then insert card 1 and enter the PIN 42. Next go to option 3 (transfer) and choose to transfer from savings(2) to checking(1). Transfer $20. d) The expected outcome was that the receipt would display that is transferred $20. e) The actual output was that the receipt said it transferred $19.50 instead. | 3 | Resolved | 3 | Normal | 63776 | 1.0 |  |  | 319847 | Aninda Shome | 319847 | Aninda Shome | Jan. 24, 2022 16:04 |  | 319847 | Aninda Shome | Jan. 25, 2022 16:32 | 0 | 0
3648521 | 68344 | ATM Project | 20 | ATM_1-20 | 292689 | Bug | 92565 | Manuel Testing | 63776 | 1.0 | Correct re-entry of PIN on the third try is accepted | MFT 40. a. The function being tested (e.g., Login) - functionality being tested is if the Correct re-entry of PIN on the third try is accepted b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) -Request to re-enter PIN is being displayed c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter incorrect pin twice and then correct PIN again d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) Allow for access e. What was the actual outcome Tells the user to "Please enter your PIN Then press ENTER" | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319959 | Ibrahim Asad | 319844 | LAB1-6 | Jan. 25, 2022 15:34 |  | 319844 | LAB1-6 | Jan. 25, 2022 16:30 | 0 | 0 | Jan. 25, 2022 16:30 LAB1-6 Defect still exists in version 1.1
3644888 | 68344 | ATM Project | 6 | ATM_1-6 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Entered Incorrect PIN then Correct PIN | a. The function being tested (e.g., Login) - functionality being tested is the Login Pin for Card 1 after putting the incorrect PIN first. b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) - System is on and is waiting for customer to enter PIN c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter Correct Card Number "1", enter incorrect PIN, "23", the first time and then enter the correct PIN "42" and then enter the correct PIN "42" again to gain access to the account. d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) At First customer Should be able to retry entering PIN and output “PIN was incorrect Please re-enter your PIN Then press ENTER”. They then enter the Correct PIN of 42 to gain access to the account without having to type it in again the second time. e. What was the actual outcome - Does not give access to account right after entering correct PIN afterward until after second time inputting correct PIN Second Time | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319959 | Ibrahim Asad | 319959 | Ibrahim Asad | Jan. 24, 2022 15:58 |  | 319844 | LAB1-6 | Jan. 25, 2022 16:30 | 0 | 0 | Jan. 25, 2022 16:30 LAB1-6 Defect still exists in version 1.1
3644848 | 68344 | ATM Project | 1 | ATM_1-1 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Input PIN for Card No: 1, 042 | a. The function being tested (e.g., Login) - functionality being tested is the Login Pin for Card 1. b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) - System is on and is waiting for customer to enter PIN c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter Correct Card Number "1", and add a single 0 before the PIN, such as 042. d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) - Should be able to retry entering PIN and output “PIN was incorrect Please re-enter your PIN Then press ENTER”. e. What was the actual outcome - Gives access to account and details. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319959 | Ibrahim Asad | 319959 | Ibrahim Asad | Jan. 24, 2022 15:49 |  | 319844 | LAB1-6 | Jan. 25, 2022 16:30 | 0 | 0 | Jan. 25, 2022 16:30 LAB1-6 Defect still exists in version 1.1
3644850 | 68344 | ATM Project | 2 | ATM_1-2 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Input PIN for Card No: 1, 0042 | a. The function being tested (e.g., Login) - functionality being tested is the Login Pin for Card 1. b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) - System is on and is waiting for customer to enter PIN c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter Correct Card Number "1", and add a two 0's before the PIN, such as 0042. d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) - Should be able to retry entering PIN and output “PIN was incorrect Please re-enter your PIN Then press ENTER”. e. What was the actual outcome - Gives access to account and details. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319959 | Ibrahim Asad | 319959 | Ibrahim Asad | Jan. 24, 2022 15:50 |  | 319844 | LAB1-6 | Jan. 25, 2022 16:29 | 0 | 0 | Jan. 25, 2022 16:29 LAB1-6 Defect still exists in version 1.1
3644945 | 68344 | ATM Project | 10 | ATM_1-10 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Withdraw Insufficient amount from Checking | a. The function being tested (e.g., Login) - functionality being tested is the withdrawal of an amount greater then the amount they have b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) - System is on and is waiting for customer to choose option to withdraw c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter Correct Card Number "1", Enter Correct PIN "42", Select 1 to Withdraw, Select 1 to withdraw from Checking, Select 5 to withdraw amount that is greater than the one you have (User only has 100 so therefore they cannot withdraw an amount of 200). d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) - Should prompt the user with “Insufficient cash available” e. What was the actual outcome - Withdraws an amount of $20 instead form Checking Account. | 3 | Resolved | 3 | Normal | 63776 | 1.0 |  |  | 319849 | Sanchit | 319959 | Ibrahim Asad | Jan. 24, 2022 16:09 |  | 319849 | Sanchit | Jan. 25, 2022 16:29 | 0 | 0
3644866 | 68344 | ATM Project | 4 | ATM_1-4 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Input PIN for Card No: 2, 01234 | a. The function being tested (e.g., Login) - functionality being tested is the Login Pin for Card 2. b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) - System is on and is waiting for customer to enter PIN c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter Correct Card Number "2", and add a single 0 before the PIN, such as 01234. d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) - Should be able to retry entering PIN and output “PIN was incorrect Please re-enter your PIN Then press ENTER”. e. What was the actual outcome - Gives access to account and details. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319959 | Ibrahim Asad | 319959 | Ibrahim Asad | Jan. 24, 2022 15:52 |  | 319844 | LAB1-6 | Jan. 25, 2022 16:29 | 0 | 0 | Jan. 25, 2022 16:29 LAB1-6 Defect still exists in version 1.1
3644867 | 68344 | ATM Project | 5 | ATM_1-5 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Depositing Money into Checking Account Test | a) The functionality being tested is depositing money into the checking account. b) The system is on, displaying the amount you wish to deposit. c) Input any amount of $20 bills into machine after pressing on. Then insert card 1 and enter the pin 42. Deposit $40 into checking account. Then deposit $20 into the checking account. d) The expected outcome is that the balance of the checking account should display $160 on the receipt. e) The actual outcome was that on the receipt it displayed the balance of the account to be 140. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319847 | Aninda Shome | 319847 | Aninda Shome | Jan. 24, 2022 15:54 |  | 319847 | Aninda Shome | Jan. 25, 2022 16:28 | 0 | 0 | Jan. 25, 2022 16:27 Aninda Shome Defect still exists in version 1.1 | Jan. 25, 2022 16:28 Aninda Shome The bug is the same, the total balance is calculated incorrectly, however it is calculated incorrectly different in 1.1 than the previous 1.0 version.
3648517 | 68344 | ATM Project | 19 | ATM_1-19 | 292689 | Bug | 92565 | Manuel Testing | 63776 | 1.0 | System performs a legitimate inquiry transaction properly | MFT 34. a. The function being tested (e.g., Login) - functionality being tested is the Inquiry for Card 1 b. The initial state of the system (e.g., System is on and is idle, i.e., not already serving a customer) - System is displaying menu of transactions types c. Steps to reproduce the defect/bug (e.g., Insert a card, then enter correct card number and PIN) - Insert Card, Enter Correct Card Number "1", enter the correct PIN "42", then select Inquiry and then choose Checking. d. What was the expected outcome? (e.g., the system successfully accepts the customer, and shows the banking menu) The Receipt for Card 1 Checking account balance should come out. e. What was the actual outcome The Receipt for Card 2 Checking account balance came out. | 2 | In Progress | 3 | Normal | 63776 | 1.0 |  |  | 319959 | Ibrahim Asad | 319844 | LAB1-6 | Jan. 25, 2022 15:30 |  | 319844 | LAB1-6 | Jan. 25, 2022 16:28 | 0 | 0 | Jan. 25, 2022 16:28 LAB1-6 Defect still exists in version 1.1
3644940 | 68344 | ATM Project | 8 | ATM_1-8 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Balance Inquiry Test 2 | a. Checking the amount of money in the money market account for Card 1. b. ATM is on the Account to inquire from screen after selecting Balance Inquiry as the transaction type. c. Turn on the system and input 5 as the amount of $20 bills. Insert card 1 and input PIN as 42. On the transaction type screen, input transaction type 4. Then, input 2 for a balance inquiry on the Money Market account. d. ATM should have displayed that the account does not exist. There is no Money Market account for Card 1 and it is not possible to do a balance inquiry on an account that doesn't exist. e. The ATM first displays Unknown Error, and then dispenses $500 regardless of the amount of money in the ATM. It then prints a receipt of the balance in the Savings account of Card 1. | 3 | Resolved | 3 | Normal | 63776 | 1.0 |  |  | 319849 | Sanchit | 319849 | Sanchit | Jan. 24, 2022 16:05 |  | 319849 | Sanchit | Jan. 25, 2022 16:24 | 0 | 0
3644851 | 68344 | ATM Project | 3 | ATM_1-3 | 292689 | Bug | 92563 | Exploratory Testing | 63776 | 1.0 | Balance Inquiry Test | a. Checking available accounts for a balance inquiry for Card 1. b. System is waiting for the user to select a transaction type (Withdrawal, Deposit, Transfer, Balance Inquiry). c. Turn on the system, and input 5 as the amount of $20 bills. Insert card 1 and input PIN as 42. On the transaction type screen, input transaction type 4. d. ATM should have displayed two accounts, being Checkings and Savings. This is because Card 1 only has these two accounts. e. ATM displays two accounts, being Checkings and Money Market. However, Card 1 does not have a Money Market account. | 3 | Resolved | 3 | Normal | 63776 | 1.0 |  |  | 319849 | Sanchit | 319849 | Sanchit | Jan. 24, 2022 15:50 |  | 319849 | Sanchit | Jan. 25, 2022 16:23 | 0 | 0